| District | Lonsdale | Operating Unit | Whole District | Update |  |
| --- | --- | --- | --- | --- | --- |

| Obj. | Key Objective | Planned Actions | Progress | Lead |
| --- | --- | --- | --- | --- |

| VISION 2018 – To make a positive impact on communities |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1.1 | Encourage & develop programme activities and service projects which engage our membership in their local & global communities | - Develop and maintain a District Nights Away Competition - Maintain an up-to-date Activity Instructor Directory - Develop Groups of interested people in certain activities and train and support to achieve permits. - Develop an A-Z of activities for each section with links to permit holders for activities and places to visit. Including more local terrain 0 walks, class c waters etc. - Undertake a programme review and restructure of the District Programme. - Deliver an annual high-profile public event (St. George’s Day) |  |  |
| 1.2 | Enhance relationships with Public, Private and 3rd Sector organisations and individuals in Lancashire for mutual benefit | - Engage more closely with the CVS- aiming to have a committee member elected. - Identify opportunities to build a relationship with the council, universities and MPs. - Host an ‘external’ event, for us to show case Scouting to local civic leaders - Form an external relations working group to identify, presidents, vice presidents and Scouting ambassadors who can help maintain and manage our external partnership. - Identify Scouting Ambassadors - Develop resources based partnership with a focus on meeting space and activity facilities. - Make the partnerships information available to groups through an online system - Take an active, high profile role in Morecambe Carnival and equivalent events. |  |  |
| 1.3 | Strengthen the brand and image of Lonsdale Scouts to increase our standing within the wider community | - Develop a social media strategy for the whole District including Scout Groups. All groups to have an online presence. - Form a recruitment team, who can lead school recruitment, attend community events and have a full range of branded resources to support them. - Recruit a Media Development Manager to establish and maintain a good working relationship with local media outlets. - Provide lonsdalescouts domain e-mail addresses to all District appointments. - Provide branded templates for letters etc to help leaders communicate on brand. - Purchase and install clearer HQ signage at all District Premises. - Carry out a visibility evaluation and provide support to groups to improve their visibility. - Improve brand visibility of all Scout Premises with clear signage. - Review photos and promotional materials within meeting places to - ensure on-brand messaging - Purchase Sail/Feather flags and pop-up banners branded as Lonsdale Scouts and explore other branded promotional material. - District and Groups to provide funding for "informal" uniform items in addition to formal uniform for adult volunteers. - Provide branded items that volunteers can take to work, i.e. mugs, phone covers - Create a youth-focussed website for our members as well as prospective members - Recruitment team to develop resources and activities to attend a full range of community events. - Weekly column in the Community Scene of the Lancaster Guardian/ Morecambe Visitor. - Develop the media team, to have one news story per month. - Create a recruitment team of trained volunteers who are equipped to attend a range of community events. - Launch a smart phone app |  |  |
| VISION 2018 – To embrace and contribute to social change |  |  |  |  |
| 2.1 | Encourage a culture of flexible volunteering to enable more adults to engage with Scouting in West Lancashire | - Advertise all District roles- being clear on the time requirements - Show case some excellent examples of flexible volunteering. - Regular helpers to be recorded as Section Assistants, not Occasional Helpers. - To be more flexible in the delivery of Modules 1-3 through use of GSLs and other trainers - Identify a Training Adviser for every adult undergoing training and better utilise prior learning accreditation when appropriate. - Ensure every adult undergoing training has a Personal Learning Plan - Establish a skills database including internal and external volunteers and organisations and make this available online for all leaders to best utilise existing skills in the district. - Ask all parents complete a skills form when their children join Scouting and ask whether they would be prepared to assist by utilising their skills occasionally. All groups to have an on-brand welcome pack that promotes adult and parental involvement. - Annual GSL session devoted to parental recruitment and involvement to share best practice. |  |  |
| 2.2 | Demonstrate and promote the use of technology, particularly social media, to support all levels of Scouting | - All groups to have a social networking presence, operated by trained individuals. - The District to have two large social networking/recruitment campaigns a year. - Use technology to make better use of volunteer’s time including - providing a conference call facility and training in its use. - Run training sessions on web technology, and also related legislation to support groups. - Have Wi-Fi in meeting places and District HQ to encourage social media usage and to support programme |  |  |
| 2.3 | Develop alternative ways of accessing Scouting, both as a young person and as an adult volunteer | - Forge closer links with schools to access more young people. - Develop a Saturday Scouting Group - Develop summer provision at the campsites. ‘Summer camp’ - Advertise short-term project roles rather than permanent roles. - Develop a team of ‘Supply leaders’ who can cover short- term absences - Re-establish the Scout Group at Morecambe Road School. - Develop a District Hardship Fund - All adults to have a role description with indicate honest time commitments. |  |  |
| VISION 2018 – To prepare Young People to be active citizens |  |  |  |  |
| 3.1 | Engage more young people in citizenship activities in the wider community | - All groups to engage in Scout Community Week - District to liase with organisations to generate mutually beneficial projects - Create a list of programmes that support citizenship. - Engage with the local your forums and youth mayor projects. - Develop and maintain external relations with other organisations that support the development of young people. |  |  |
| 3.2 | Increase the number of Young Leaders | - Develop links with School DofE Contacts - Aim for two young leaders per section and develop a talent list in the Scout Section for future young leaders. - Develop specific young leader recruitment resources. - Establish a Group YL mentor in every group. - Develop an online registration process for young leaders. - Use social networking to continually engage with young leaders. |  |  |
| 3.3 | Enable more young people to access opportunities as global citizens | - Offer additional support through leaders meetings to help leaders take young people abroad. - Ensure the County trips are well advertised and young people are supported to apply. - Identify young people who would benefit from international trip and sign post them to it. - Provide support and opportunities for District led trips on a three year cycle. - Promote the District International Fund and formalise the application process and promote on our website. - Engage with different organisations – trade craft, fair trade, shelter box to enhance our programme - Ensure the Explorer programme provides developmental opportunities for Gap Years etc. - Provide an annual home based international event – JOTA/ JOTI - Encourage all members to take part in the county International Staged Activity badge to increase Global Awareness. Set up a linking scheme where links can be set up with Scout Groups around the World. |  |  |

| VISION – To be enjoyed by more young people and more adult volunteers |  |  |  |  |
| --- | --- | --- | --- | --- |
| 4.1 | Increase our membership overall across all sections and adults by 4% | - Hold a reunion for ex leaders. - Develop second sections in existing Scout groups. - Through promotion and recruitment for a 15% impact rate in primary schools. - Promote female membership in all promotional material. - Use National Census information to open/Develop Scout Groups in areas new housing areas (Heysham/ Standen Park) - All groups to have a group development plan and linking plan. - Groups to work with their partnering schools to ensure that all schools know about Scouting. - Opening of new Groups on The Ridge, Westgate, Galgate. With additional Explorer Scout Units. - All groups to hold annual open nights. - Central management of waiting lists. - Every group to hold a family camp every two years. - Implement parent Rotas in all sections where possible - Identify parent’s skills and attempt to recruit to suitable roles including leadership and Exec Committees - Identify and train 20 Training Advisers in the District to increase the numbers of leaders completing training. - Establish link with the Job Centre and other recruitment agencies to promote volunteering opportunities as good experience |  |  |
| 4.2 | To continue to develop resources, facilities and a skills base for young people to access Everyday Adventure | -Develop a 5 year/ 10 year business plan for our activity centres that ensures they are fit for purpose, support our programme and our financially viable. - Offer grant advice support to Scout HQs in need of repair. - Invest in the training of adults to gain NGB Activity Qualifications and encourage closer working between sections. - Develop the activity provision at the activity centres. - Offer badge days for ‘difficult badges’ - Have an annual skills and chills event and district camp on an annual basis to support skills. - Promote skills training and identify specialists in the programme A-Z who can support. |  |  |
| 4.3 | Provide support to all adults to ensure they are well equipped and valued in their role so they enjoy volunteering with Lonsdale Scouts | - Increase the number of adults receiving good service awards. - Host an annual social event to thank leaders. - Develop the leadership and management of Scout Groups so that all groups have group committees and effective Group Scout Leaders. - Hold an annual group management support forum. - Every section in the District visited by a DC/DDC/ADC twice each year - Organise free social events for volunteers across the district. - Notify Sectional ADCs of all new sectional leaders and assistant leaders starting. - Develop and produce an induction pack and induction programme for new leaders (different to training) - Carry out District all Leaders meetings at least termly. (3 per year) - Groups to Carry out Group all Leaders meetings at least termly. (Including Young Leaders) - Provide funding for externally recognisable skills and training. - Carry out Exit Interviews and feed the outcomes back to a central database to be reviewed by District Team and Appointments Committee to establish why people leave. |  |  |
| VISION – To be shaped by young people in partnership with adults |  |  |  |  |
| 5.1 | Increase the role and participation of young people in the leadership, management and administration of Scouting | - Two under 25’s on all committees - Develop a ‘talent list’ of younger adults and mentors to pass on skills. - Use the AGSL role and DL roles to develop talent. - Ensure young leaders are invited to section meetings and monitor numbers attending. - Explorer Forum/ Patrol Leaders forum invite to full district leader meeting. - Develop the role of a District Youth Commissioner - Appoint young leaders to the District Section Teams - Share examples and ideas for youth involvement in Beavers and Cubs - All District Events to have a strong presence of young people leading activities (ie. Leading St George’s Day service) |  |  |
| 5.2 | Encourage the creation and greater participation in meaningful youth forums in our 6-25 programme provision | - Strengthen the Explorer Forum and Patrol Leaders forum and ensure they have direct influence. - Provide training and support to encourage leaders to have section youth forums and give young people greater responsibility for the programme. - Hold regular sectional forum events at District level with genuine power for programme decisions - Engage Young Leaders to help run youth forums and youth involvement in programme planning - Use a "You said, we did" technique when promoting programmes to youth members. |  |  |
| 5.3 | Develop the support tools and resources to assist adults to involve young people in opportunities that shape Scouting in Lonsdale Scouts | - Develop some ‘Champions’ to offer support on how to involve young people. - Demonstrate good youth involvement at all levels of the District. - Make a focus for leaders meeting. |  |  |
| VISION 2018 – As diverse as the communities in which we live |  |  |  |  |
| 6.1 | By Interpreting available data, determine the diversity of our community and identify the potential of Scouting within that diversity. | - Analyse the available data, and look at areas where there is a high population of: - BME Groups - Children with Special Needs - Children from a Socially or Economically disadvantaged background - Looked After Children - All sections to be fully co-educational with male and female members by the end of 2018 - All recruitment material to reflect our diversity. - Engage contacts in different communities who can provide advice and support to enable us to reach more young people. - Ensure that Church parades in all groups are optional. - Develop Saturday Scouting. |  |  |
| 6.2 | Where appropriate, create a framework of support to enable Scouting to embrace the diversity of our community. | - Create provision that meets on Saturdays. - Re-establish the group at Morecambe Road School - Advertise directly to different BME Communities / LGBT Groups - Work with the Police to offer summer provision for children from the most disadvantaged backgrounds. - Develop a District Hardship Fund - Develop a Second Hand Uniform Shop - Provide promotional materials in different languages. - Promote the use of alternative promises. - St George’s Day to be fully inclusive. |  |  |
| 6.3 | Engage with groups that represent the diversity of our community and help understand the opportunities of developing relationships within those diverse groups. | - Engage with PACT meetings - Liase with the CVS to develop contacts. - Invite leaders of different faith groups to our St George’s Day and offer a reception afterwards. - Engage with the different societies at the Universities to support programme activities that support diversity. - Provide additional training and support to leaders who work with different groups. |  |  |